Earned Value Situation for Project.

Task

Original Budget

BCWS

ACWP

| BCWP |
| --- |
| A | $20,000 | $20,000 | $15,000 | $20,000 |
| B | $25,000 | $20,000 | $19,000 | $20,000 |
| C | $16,000 | $16,000 | $15,000 | $16,000 |
| D | $18,000 | $15,000 | $2,500 | $1,800 |
| E | $10,000 | $5,000 | $3,000 | $3,000 |
| F | $20,000 | $0 | $3,000 | $4,000 |
| Total | $109,000 | $76,000 | $57,500 | $64,800 |

Project planned Duration was originally 10 months.

BCWS = Budgeted cost of work scheduled ( What we thought it would cost to do what we had planned to do by now )

ACWP = Actual cost of work performed ( What it actually cost to do what we have done by now )

BCWP = Budgeted cost of work performed ( What we thought it would cost to do what we have actually done now )

CV = Cost Variance ( The difference between what we thought it would cost to do this much work and what it did cost )

SV = Schedule Variance ( or time variance ) ( The difference between how muck work we thought we could get done for this cost and how much we have done )

BAC = Budget at Completion ( Original planned budget of the project )

TAC = Time at Completion ( Original planned duration of the project )

Project Status Calculations based on the figures provided in the table above,

CV = BCWP- ACWP = $64,800 - $57,500 = $7,300  under budget or 11% under budget ( 89% spent )

SV = BCWP - BCWS = $64,800 - $76,000 = ( - $11,200 ) behind schedule or over time

ECAC = ( ACWP / BCWP ) x BAC = ( $57,500 / $64,800 ) x $109,000 = $96,721 est cost at completion

ETAC = ( BCWS / BCWP ) x TAC = ( $76,000 / 64,800 ) x 10 months = 11.73 months to completion

Conclusion = Project is projected to be under budget but over time.